# Producing AMRO
Producing AMRO goes hand in hand with the program development.
## Dates
AMRO takes place in Mid may, the dates given by the thursday, which is usually a holiday in Austria.
Final dates are usually decided in coordination with main venue afo.
## Locations
Venues where AMRO takes place
1. afo - architekturforum oberösterreich
2. STWST stadtwerkstatt linz
Additional venues (in the last couple of editions)
1. bb15
2. DH5
3. MAERZ
4. Willy*fred
5. /dev/lol/
some AMRO editions also took place at:
1. Time's up
2. Frisiersalon (installation)
3. Kunstraum Goethestrasse
Wishlist Location:
SPLACE am hauptplatz
## Timing
see Timeline
In a nutshell, production starts slowly generally 4-6 months before the event.
Around 2 months before AMRO production gets more and more intense till a month before festival, where things go in print & program is published online. At that point everything should be kind of standing, last breathing before everyone arrives and the festival happens.
Generally two/three days after the festival workloads reduces to administration and reports. In general one or two months after the festival the documentation video and pictures are uploaded on the website, marking the closing of production.
## Timetable
## Communication
## Hosting
### Stays
### Drinks and food
Return: only full or completely empty crates will be picked up by drinks distributors. Half empty crates are counted as empty.
## Setup
## Materials