# AMRO Timeline
## Fall & Winter 20XX-2/20XX-1
Preparation research lab 20xx-1 program. AMRO Program ideas are collected.
# Spring 20XX-1
Define AMRO 20XX dates, connect with Kunstuni & begin booking festival venues.
# June 20XX-1
# July 20XX-1
Research Lab activities, slowly collecting names for AMRO.
Begin securing people and locations
# August 20XX-1
# September 20XX-1
- Produce Funding application (Bund) for upcoming year
- At events such as Ars Electronica, network & announce dates. Maybe one flyer?
- Maybe publish an early open call for participation?
# October 20XX-1
- Mid of the month: First funding application Bund (→ servus team)
- End of the month: close the open call for next year
# November 20XX-1
- Open Call application sorting & Jury process.
- Begin invitations for curated keynotes / lectures.
# December 20XX-1
- End of december, moment of the year when Bund gives us info about next year's budget.
- In past editions we waited the communication of the funding before starting the Open Call process. It does not have to be.
# January 20XX
- often open call text prepared in mid/end January. It can happen earlier.
- Definition travels / stays.
# February 20XX
often application went out around beginning/mid February.
# March 20XX
# April 20XX
- Goal is to publish the final final program ~4 weeks before the festival.
- Website updated, webforms for participation ready.
# May 20XX
It's happening. Everything comes all at once. All the people will be happy to help, you need to tell them what to do.
# Post-May 20XX
- AMRO financial
- Collect & publish documentation